## Backlog
ID | Area | Priority | Effort | Task | Description | Status
B-01 | Portfolio | High | L | Rewrite project pages as case studies | SCAFFOLDED + placeholder content filled for all 9 projects EN+RU. Pages live at /works/[slug] and /ru/works/[slug] with full case study layout. View-transition morph from gallery cover wired. NOW NEEDS: replace placeholder facts/quotes/metrics with real client data — see B-19 for per-project content pass. | In progress
B-19 | Content | High | L | Replace placeholder case study content with real data | All 9 case studies have filled placeholder content (src/content/works/{en,ru}/*.md). Need real pass: verify years/roles/stacks, add real client quotes (testimonials), add real outcome metrics, add gallery images per project, confirm or add live URLs. Do one project at a time — change draft: false to draft: true to hide unfinished ones if needed. | Backlog
B-02 | Performance | Medium | L | Migrate Spline scene to raw three.js | Spline viewer ships ~2-3MB and hurts first paint on mobile/4G. Export the elk scene and render with three.js directly. Keeps the visual, cuts the weight. | Backlog
B-03 | SEO/Social | Medium | M | OG-image + full social meta | Generate an OG preview image (1200x630) with 3D elk + Elkhovering wordmark. Add og:title, og:description, og:image, og:url, twitter:card meta tags in Layout. Affects how links look in Telegram, Twitter, LinkedIn. | Backlog
B-04 | Copy | High | S | Finalize hero tagline per new positioning | DONE. Hero H1 -> 'Creative director', tagline -> 'The art director you hire before you need a team'. Applied in en.json, ru.json, Hero.astro fallback. | Done
B-05 | Copy | High | M | Rewrite About as manifesto (reuse resume copy) | DONE. About rewritten using CV copy: intersection of IT/product/digital, 300+ projects, walk into chaos, leave stable platform. Personality bit now: economic strategy games + gardening + game design at Syrnik.dev. | Done
B-06 | Services | Medium | M | Reduce services 6 -> 2-3 | Current list (creative sites / brand / NFT / consulting / team lead / lectures) spans 3 different businesses. With positioning now fixed ('art director before the team'), consolidate into primary offer (fractional digital lead) + 1-2 adjacent. | Backlog
B-07 | Trust | High | M | Add testimonials section | Pull 2-3 short quotes from the 3 recommendations in CV (Мастер рекламы, Р-Групп, Nut Valley Armenia). Add a clean testimonials block between Works and Services or between Services and Contacts. | Backlog
B-08 | Trust | Medium | S | Add client logos row | Even 5-6 monochrome logos of past clients (Heavens.pro alumni, Syrnik, Custom, etc) gives instant credibility. Usually sits above-the-fold or in About. | Backlog
B-09 | CTA | Medium | S | Resolve LinkedIn / Behance empty links | Social row in Contacts still has empty href="" for linkedin and behance. Either remove them, or point to real profiles. Currently dead clicks. | Backlog
B-17 | CMS | High | L | Admin panel for editing case studies | Content lives in src/content/works/{en,ru}/*.md with strict Zod schema — editable in any git-based CMS. Research & pick: Decap CMS (open, git-based, needs GitHub OAuth proxy for shared hosting), Tina (visual, free tier), Sanity/Contentful (external API). Must preserve existing frontmatter fields, support EN+RU parallel editing, and let non-devs add galleries/update URLs/toggle draft without touching git directly. | Backlog
B-18 | i18n | Medium | M | Unify i18n strategy (client-side vs URL-based) | DONE. Unified on client-side i18n via html[data-lang] across the whole site. Both EN and RU blocks coexist in every HTML page (chrome via data-i18n, case studies via [data-case-lang] wrappers), CSS toggles visibility. Inline early script in <head> sets data-lang from localStorage before first paint to avoid FOUC. Old /ru/ paths redirected for backwards compat. | Done
B-16 | CTA | High | M | Redesign Contacts — Telegram-primary without breaking composition | Current Contacts restored to original (big H1 = copyable email, small row = or/telegram/linkedin/behance). But Telegram is the actual primary CTA per positioning. Need a redesigned block that makes Telegram the hero action while preserving the designer-grade composition Eugene values. Likely variations to prototype: (a) big @elkhovering H1 + email as secondary copyable, (b) split H1 with both, (c) asymmetric two-column. Design-first, not markup-first. | Backlog
B-10 | Deploy | High | M | Update GitHub Actions deploy for Astro build | DONE. Workflow now runs npm ci + npm run build, then SFTPs dist/ to public_html with mirror semantics — uploads build output and prunes orphans (old index.html, style.css, script.js from pre-Astro). Preserves cgi-bin / .well-known / server-managed .htaccess. | Done
B-11 | Cleanup | Low | S | Remove legacy root files after Astro is verified | Delete index.html, style.css, mobile.css, script.js, nav.html, works.html from repo root once the Astro build is confirmed working in production. Keep as git history. | Backlog
B-12 | Features | Low | M | Contact form as alternative to Telegram | For clients who prefer email-first flow. Use Formspree or similar (no backend on shared hosting). Low priority since Telegram is primary CTA. | Backlog
B-13 | Content | Medium | L | Per-project data: role, stack, year, outcome | DONE. Schema finalized in src/content.config.ts — frontmatter covers slug/title/summary/year/role/url/client/stack/tags/cover/gallery/draft. Layout-only meta (col/row/rellax/layer) stays in src/data/works.js. Filling real values is a content task under B-01. | Done
B-14 | UX | Low | S | Mobile layout pass | Current mobile.css handles basics but wasn't tested against new Astro components. Do a proper responsive review when content is final. | Backlog
B-15 | Analytics | Low | S | Add lightweight analytics | Plausible or Umami (privacy-first, no cookie banner needed). Just to know which works get clicks and where visitors come from. Not GA. | Backlog